## RACI
| Bord members of StC | Chairman of the StC. | Business expert | Project manager | Architect | Useability expert | Development team | Test manger | Test team | Chief of operations | Operational staff
Scope/Business clarification | I | A | R | C | C | C | I | I |  | I
Changes to scope | C | A | R | C | C | C | I | I | I
Project planning | C | A | C | R | C | C | C | C | I | I | I
Development | C | A | I | R | I | C | R | I | I | I | I
Test planning | I | I | C | C | C | I | I | A | I | I | I
Testing | I I C R: C; I I C I: A; I I I I: R; I I I I: C; I I I I: I
Deployment | I I C R: C; I I C I: C; I I I I: I; I I I I: A; I I I I: R

## About
RACI is an English abbreviation for Responsible, Accountable, Consulted and Informed. Each letter of the acronym represents a level of task responsibility.
RACI Definitions:
Responsible:
The person written here does the actual work to complete the task. Every single task must have at least one person responsible, but there can easily be more than one.
Accountable:
The person under accountable delegates the work and is the last to review the task before it is approved and finished. For some tasks, it may be that it is a person from Responsible who also acts as Accountable. It’s just important to have only one accountable person for each task.
Consulted:
Usually, the outcome of project tasks is improved if somebody else reviews the task. The persons registered under consulted are ready for consultation and will continuously give input on how something will affect future project work.
Informed:
The team members must be informed about the project’s progress and not only told some details.

## Validation
Responsible: | R
Accountable: | A
Consulted: | C
Informed: | I